## Timesheet
Datum | Sprint | Nick | Nick Comments | Valerie | Valerie Comments | Olivier | Olivier Comments | David | David Comments | TBD1 | TBD1 Comments
2017-03-27 | 1 | 0.5 | Sprint Planning | 0.5 | Sprint Planning | 0.5 | Sprint Planning | 0.5 | Sprint Planning | 0 | Not started | =WEEKDAY($A2;2)>5
2017-03-28 | 1 | 0.5 | DevOps | 1 |  | 0.8 |  | 1 |  | 0 | Not started
2017-03-29 | 1 | 0.5 | DevOps | 1 |  | 0.8 |  | 1 |  | 0 | Not started
2017-03-30 | 1 | 0.5 | DevOps | 1 |  | 0.8 |  | 1 |  | 0 | Not started
2017-03-31 | 1 | 0.5 |  | 0 | Holiday | 0.8 |  | 1 |  | 0 | Not started
2017-04-01
2017-04-02
2017-04-03 | 1 | 0.5 | DevOps | 0 | Holiday | 0.8 |  | 1 |  | 0 | Not started
2017-04-04 | 1 | 0.5 | DevOps | 1 |  | 0.8 |  | 1 |  | 0 | Not started
2017-04-05 | 1 | 0.5 | DevOps | 1 |  | 0.8 |  | 1 |  | 0 | Not started
2017-04-06 | 1 | 0.5 | DevOps | 1 |  | 0.8 |  | 1 |  | 0 | Not started
2017-04-07 | 1 | 0.5 | Review | 0.5 | Review | 0.5 | Review | 0.5 | Review | 0 | Not started
2017-04-08
2017-04-09
2017-04-10 | 2 | 0.5 | Sprint Planning | 0 | Illness | 0.5 | Sprint Planning | 0.5 | Sprint Planning | 0 | Not started
2017-04-11 | 2 | 0.5 | DevOps | 0 | Illness | 0.8 |  | 1 |  | 0 | Not started
2017-04-12 | 2 | 0.5 | DevOps | 0 | Illness | 0.8 |  | 0.5 | Holiday | 0 | Not started
2017-04-13 | 2 | 0.5 | DevOps | 0 | Illness | 0.8 |  | 1 |  | 0 | Not started
2017-04-14 | 2 | 0.5 | DevOps | 0 | Illness | 0.8 |  | 1 |  | 0 | Not started
2017-04-15
2017-04-16
2017-04-17 | 2
2017-04-18 | 2 | 0.5 | DevOps | 1 |  | 0.8 |  | 0 | Course | 0 | Not started
2017-04-19 | 2 | 0.5 | DevOps | 1 |  | 0.8 |  | 0 | Course | 0 | Not started
2017-04-20 | 2 | 0.5 | DevOps | 1 |  | 0.8 |  | 1 |  | 0 | Not started
2017-04-21 | 2 | 0 | Review & Retro | 0 | Review & Retro | 0 | Review & Retro | 0 | Review & Retro | 0 | Not started
2017-04-22
2017-04-23 | [9 empty] | 0
2017-04-24 | 3 | 0.5 | Sprint Planning | 0.5 | Sprint Planning | 0.5 | Sprint Planning | 0.5 | Sprint Planning | 0 | Sprint Planning & Intro
2017-04-25 | 3 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0 | Intro
2017-04-26 | 3 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0 | Intro
2017-04-27 | 3 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.5 | New
2017-04-28 | 3 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.5 | New
2017-04-29
2017-04-30
2017-05-01 | 3
2017-05-02 | 3 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.5 | New
2017-05-03 | 3 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.5 | New
2017-05-04 | 3 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.5 | New
2017-05-05 | 3 | 0.5 | Review | 0.5 | Review | 0.5 | Review | 0.5 | Review | 0.5 | Sprint Planning
2017-05-06
2017-05-07
2017-05-08 | 4 | 0.5 | Sprint Planning | 0.5 | Sprint Planning | 0.5 | Sprint Planning | 0.5 | Sprint Planning | 0 | Sprint Planning & Intro
2017-05-09 | 4 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.8
2017-05-10 | 4 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.8
2017-05-11 | 4 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.8
2017-05-12 | 4 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.8
2017-05-13
2017-05-14
2017-05-15 | 4 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.8
2017-05-16 | 4 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.8
2017-05-17 | 4 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.8
2017-05-18 | 4 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.8
2017-05-19 | 4 | 0.5 | Review | 0.5 | Review | 0.5 | Review | 0.5 | Review | 0.5 | Sprint Planning
2017-05-20
2017-05-21
2017-05-22 | 5 | 0.5 | Sprint Planning | 0.5 | Sprint Planning | 0.5 | Sprint Planning | 0.5 | Sprint Planning | 0 | Sprint Planning & Intro
2017-05-23 | 5 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.8
2017-05-24 | 5 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.8
2017-05-25 | 5
2017-05-26 | 5 | 0 | Brug | 0 | Brug | 0 | Brug | 0 | Brug | 0 | Brug
2017-05-27
2017-05-28
2017-05-29 | 5 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.8
2017-05-30 | 5 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.8
2017-05-31 | 5 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.8
2017-06-01 | 5 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.8
2017-06-02 | 5 | 0.5 | Review | 0.5 | Review | 0.5 | Review | 0.5 | Review | 0.5 | Sprint Planning
2017-06-03
2017-06-04
2017-06-05 | 6
2017-06-06 | 6 | 0.5 | Sprint Planning | 0.5 | Sprint Planning | 0.5 | Sprint Planning | 0.5 | Sprint Planning | 0 | Sprint Planning & Intro
2017-06-07 | 6 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.8
2017-06-08 | 6 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.8
2017-06-09 | 6 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.8
2017-06-10
2017-06-11
2017-06-12 | 6 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.8
2017-06-13 | 6 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.8
2017-06-14 | 6 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.8
2017-06-15 | 6 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.8
2017-06-16 | 6 | 0.5 | Review | 0.5 | Review | 0.5 | Review | 0.5 | Review | 0.5 | Sprint Planning
2017-06-17
2017-06-18
2017-06-19 | 7 | 0.5 | Sprint Planning | 0.5 | Sprint Planning | 0.5 | Sprint Planning | 0.5 | Sprint Planning | 0 | Sprint Planning & Intro
2017-06-20 | 7 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.8
2017-06-21 | 7 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.8
2017-06-22 | 7 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.8
2017-06-23 | 7 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.8
2017-06-24
2017-06-25
2017-06-26 | 7 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.8
2017-06-27 | 7 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.8
2017-06-28 | 7 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.8
2017-06-29 | 7 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.8
2017-06-30 | 7 | 0.5 | Review | 0.5 | Review | 0.5 | Review | 0.5 | Review | 0.5 | Sprint Planning
2017-07-01
2017-07-02
2017-07-03 | 8 | 0.5 | Sprint Planning | 0.5 | Sprint Planning | 0.5 | Sprint Planning | 0.5 | Sprint Planning | 0 | Sprint Planning & Intro
2017-07-04 | 8 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.8
2017-07-05 | 8 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.8
2017-07-06 | 8 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.8
2017-07-07 | 8 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.8
2017-07-08
2017-07-09
2017-07-10 | 8 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.8
2017-07-11 | 8 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.8
2017-07-12 | 8 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.8
2017-07-13 | 8 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.8
2017-07-14 | 8 | 0.5 | Review | 0.5 | Review | 0.5 | Review | 0.5 | Review | 0.5 | Sprint Planning
2017-07-15
2017-07-16
2017-07-17 | 9 | 0.5 | Sprint Planning | 0.5 | Sprint Planning | 0.5 | Sprint Planning | 0.5 | Sprint Planning | 0 | Sprint Planning & Intro
2017-07-18 | 9 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.8
2017-07-19 | 9 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.8
2017-07-20 | 9 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.8
2017-07-21 | 9
2017-07-22
2017-07-23
2017-07-24 | 9 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.8
2017-07-25 | 9 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.8
2017-07-26 | 9 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.8
2017-07-27 | 9 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.8
2017-07-28 | 9 | 0.5 | Review | 0.5 | Review | 0.5 | Review | 0.5 | Review | 0.5 | Sprint Planning
2017-07-29
2017-07-30
2017-07-31 | 10 | 0.5 | Sprint Planning | 0.5 | Sprint Planning | 0.5 | Sprint Planning | 0.5 | Sprint Planning | 0 | Sprint Planning & Intro
2017-08-01 | 10 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.8
2017-08-02 | 10 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.8
2017-08-03 | 10 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.8
2017-08-04 | 10 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.8
2017-08-05
2017-08-06
2017-08-07 | 10 | 0.7 | LeadDev | 1 |  | 0 | Holiday | 1 |  | 0.8
2017-08-08 | 10 | 0.7 | LeadDev | 1 |  | 0 | Holiday | 1 |  | 0.8
2017-08-09 | 10 | 0.7 | LeadDev | 1 |  | 0 | Holiday | 1 |  | 0.8
2017-08-10 | 10 | 0.7 | LeadDev | 1 |  | 0 | Holiday | 1 |  | 0.8
2017-08-11 | 10 | 0.5 | Review | 0.5 | Review | 0 | Holiday | 0.5 | Review | 0.5 | Sprint Planning
2017-08-12
2017-08-13
2017-08-14 | 11 | 0 | Brug | 0 | Brug | 0 | Brug | 0 | Brug | 0 | Brug
2017-08-15 | 11
2017-08-16 | 11 | 0.5 | Sprint Planning | 0 | Holiday | 0 | Holiday | 0.5 | Sprint Planning | 0 | Sprint Planning & Intro
2017-08-17 | 11 | 0.7 | LeadDev | 0 | Holiday | 0 | Holiday | 1 |  | 0.8
2017-08-18 | 11 | 0.7 | LeadDev | 0 | Holiday | 0 | Holiday | 1 |  | 0.8
2017-08-19
2017-08-20
2017-08-21 | 11 | 0.7 | LeadDev | 0 | Holiday | 1 |  | 1 |  | 0.8
2017-08-22 | 11 | 0.7 | LeadDev | 0 | Holiday | 1 |  | 1 |  | 0.8
2017-08-23 | 11 | 0.7 | LeadDev | 0 | Holiday | 1 |  | 1 |  | 0.8
2017-08-24 | 11 | 0.7 | LeadDev | 0 | Holiday | 1 |  | 1 |  | 0.8
2017-08-25 | 11 | 0.5 | Review | 0 | Holiday | 0.5 | Review | 0.5 | Review | 0.5 | Sprint Planning
2017-08-26
2017-08-27
2017-08-28 | 12 | 0.5 | Sprint Planning | 0.5 | Sprint Planning | 0.5 | Sprint Planning | 0.5 | Sprint Planning | 0 | Sprint Planning & Intro
2017-08-29 | 12 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.8
2017-08-30 | 12 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.8
2017-08-31 | 12 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.8
2017-09-01 | 12 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.8
2017-09-02
2017-09-03
2017-09-04 | 12 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.8
2017-09-05 | 12 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.8
2017-09-06 | 12 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.8
2017-09-07 | 12 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.8
2017-09-08 | 12 | 0.5 | Review | 0.5 | Review | 0.5 | Review | 0.5 | Review | 0.5 | Sprint Planning
2017-09-09
2017-09-10
2017-09-11 | 13 | 0.5 | Sprint Planning | 0.5 | Sprint Planning | 0.5 | Sprint Planning | 0.5 | Sprint Planning | 0 | Sprint Planning & Intro
2017-09-12 | 13 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.8
2017-09-13 | 13 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.8
2017-09-14 | 13 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.8
2017-09-15 | 13 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.8
2017-09-16
2017-09-17
2017-09-18 | 13 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.8
2017-09-19 | 13 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.8
2017-09-20 | 13 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.8
2017-09-21 | 13 | 0.7 | LeadDev | 1 |  | 1 |  | 1 |  | 0.8
2017-09-22 | 13 | 0.5 | Review | 0.5 | Review | 0.5 | Review | 0.5 | Review | 0.5 | Sprint Planning
2017-09-23
2017-09-24
2017-09-25 | 14
2017-09-26 | 14
2017-09-27 | 14
2017-09-28 | 14
2017-09-29 | 14

## Capacity
Row Labels | Sum of Nick | Sum of Valerie | Sum of Olivier | Sum of David | Sum of TBD1 | Capacity | User Stories | Delta | Committed | Ratio
1 | 5 | 7 | 7.4 | 9 | 0 | 227.2 | 221 | 6.2 | 180 | 97.27%
2 | 4 | 3 | 6.1 | 5 | 0 | 144.8 | 134 | 10.8 | 120 | 92.54%
3 | 5.9 | 8 | 8 | 8 | 3 | 263.2 | 294 | -30.8 | 264 | 111.7%
4 | 6.6 | 9 | 9 | 9 | 6.9 | 324 | 64 | 260 | 128 | 19.75%
5 | 5.2 | 7 | 7 | 7 | 5.3 | 252
6 | 5.9 | 8 | 8 | 8 | 6.1 | 288
7 | 6.6 | 9 | 9 | 9 | 6.9 | 324
8 | 6.6 | 9 | 9 | 9 | 6.9 | 324
9 | 5.9 | 8 | 8 | 8 | 6.1 | 288
10 | 6.6 | 9 | 4.5 | 9 | 6.9 | 288
11 | 5.2 | 0 | 4.5 | 7 | 5.3 | 176
12 | 6.6 | 9 | 9 | 9 | 6.9 | 324
13 | 6.6 | 9 | 9 | 9 | 6.9 | 324
Grand Total | 76.7 | 95 | 98.5 | 106 | 67.2 | 3547.2 |  |  |  | 4

## Mid Term Plan
Nr | Title | Effort | Kano | Cost of Delay | Priority | Sprint | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5
180 | As a <type of user>, I want <some goal> so that <some reason> | 5 | Performer | L3 | 2 | 1 | 5 | 0 | 0 | 0 | 0 | =IF([@Sprint]=1;[@Effort];0)
370 | As a <type of user>, I want <some goal> so that <some reason> | 25 | Exciter | L5 | 7 | 1 | 25 | 0 | 0 | 0 | 0
20 | As a <type of user>, I want <some goal> so that <some reason> | 22 | Basic | L2 | 9 | 1 | 22 | 0 | 0 | 0 | 0
260 | As a <type of user>, I want <some goal> so that <some reason> | 22 | Performer | L1 | 12 | 1 | 22 | 0 | 0 | 0 | 0
240 | As a <type of user>, I want <some goal> so that <some reason> | 40 | Performer | L4 | 13 | 1 | 40 | 0 | 0 | 0 | 0
110 | As a <type of user>, I want <some goal> so that <some reason> | 11 | Basic | L1 | 14 | 1 | 11 | 0 | 0 | 0 | 0
320 | As a <type of user>, I want <some goal> so that <some reason> | 34 | Exciter | L2 | 17 | 1 | 34 | 0 | 0 | 0 | 0
290 | As a <type of user>, I want <some goal> so that <some reason> | 38 | Performer | L4 | 22 | 1 | 38 | 0 | 0 | 0 | 0
170 | As a <type of user>, I want <some goal> so that <some reason> | 24 | Basic | L2 | 25 | 1 | 24 | 0 | 0 | 0 | 0
90 | As a <type of user>, I want <some goal> so that <some reason> | 26 | Basic | L4 | 26 | 2 | 0 | 26 | 0 | 0 | 0
40 | As a <type of user>, I want <some goal> so that <some reason> | 10 | Basic | L4 | 29 | 2 | 0 | 10 | 0 | 0 | 0
200 | As a <type of user>, I want <some goal> so that <some reason> | 10 | Performer | L5 | 36 | 2 | 0 | 10 | 0 | 0 | 0
210 | As a <type of user>, I want <some goal> so that <some reason> | 36 | Performer | L1 | 37 | 2 | 0 | 36 | 0 | 0 | 0
30 | As a <type of user>, I want <some goal> so that <some reason> | 15 | Basic | L3 | 47 | 2 | 0 | 15 | 0 | 0 | 0
130 | As a <type of user>, I want <some goal> so that <some reason> | 18 | Basic | L3 | 48 | 2 | 0 | 18 | 0 | 0 | 0
60 | As a <type of user>, I want <some goal> so that <some reason> | 4 | Basic | L1 | 58 | 2 | 0 | 4 | 0 | 0 | 0
270 | As a <type of user>, I want <some goal> so that <some reason> | 11 | Performer | L2 | 61 | 2 | 0 | 11 | 0 | 0 | 0
340 | As a <type of user>, I want <some goal> so that <some reason> | 4 | Exciter | L2 | 61 | 2 | 0 | 4 | 0 | 0 | 0
140 | As a <type of user>, I want <some goal> so that <some reason> | 29 | Basic | L4 | 71 | 3 | 0 | 0 | 29 | 0 | 0
150 | As a <type of user>, I want <some goal> so that <some reason> | 6 | Basic | L5 | 71 | 3 | 0 | 0 | 6 | 0 | 0
50 | As a <type of user>, I want <some goal> so that <some reason> | 13 | Basic | L5 | 72 | 3 | 0 | 0 | 13 | 0 | 0
230 | As a <type of user>, I want <some goal> so that <some reason> | 36 | Performer | L3 | 74 | 3 | 0 | 0 | 36 | 0 | 0
280 | As a <type of user>, I want <some goal> so that <some reason> | 4 | Performer | L3 | 74 | 3 | 0 | 0 | 4 | 0 | 0
360 | As a <type of user>, I want <some goal> so that <some reason> | 19 | Exciter | L4 | 74 | 3 | 0 | 0 | 19 | 0 | 0
70 | As a <type of user>, I want <some goal> so that <some reason> | 29 | Basic | L2 | 75 | 3 | 0 | 0 | 29 | 0 | 0
330 | As a <type of user>, I want <some goal> so that <some reason> | 20 | Exciter | L1 | 75 | 3 | 0 | 0 | 20 | 0 | 0
250 | As a <type of user>, I want <some goal> so that <some reason> | 13 | Performer | L5 | 83 | 3 | 0 | 0 | 13 | 0 | 0
300 | As a <type of user>, I want <some goal> so that <some reason> | 19 | Performer | L5 | 83 | 3 | 0 | 0 | 19 | 0 | 0
220 | As a <type of user>, I want <some goal> so that <some reason> | 11 | Performer | L2 | 87 | 3 | 0 | 0 | 11 | 0 | 0
310 | As a <type of user>, I want <some goal> so that <some reason> | 38 | Exciter | L1 | 87 | 3 | 0 | 0 | 38 | 0 | 0
190 | As a <type of user>, I want <some goal> so that <some reason> | 18 | Performer | L4 | 89 | 3 | 0 | 0 | 18 | 0 | 0
120 | As a <type of user>, I want <some goal> so that <some reason> | 39 | Basic | L2 | 91 | 3 | 0 | 0 | 39 | 0 | 0
350 | As a <type of user>, I want <some goal> so that <some reason> | 22 | Exciter | L3 | 92 | 4 | 0 | 0 | 0 | 22 | 0
100 | As a <type of user>, I want <some goal> so that <some reason> | 21 | Basic | L5 | 94 | 4 | 0 | 0 | 0 | 21 | 0
160 | As a <type of user>, I want <some goal> so that <some reason> | 11 | Basic | L1 | 94 | 4 | 0 | 0 | 0 | 11 | 0
10 | As a <type of user>, I want <some goal> so that <some reason> | 6 | Basic | L1 | 97 | 4 | 0 | 0 | 0 | 6 | 0
80 | As a <type of user>, I want <some goal> so that <some reason> | 4 | Basic | L3 | 99 | 4 | 0 | 0 | 0 | 4 | 0
Total |  | 713 |  |  |  | Committed | 221 | 134 | 294 | 64 | 0
[6 empty] | Capacity | 227.2 | 144.8 | 263.2 | 324 | 252
[6 empty] | Marge | 6.2 | 10.8 | -30.8 | 260 | 252